Meeting summary (Across/ACROS project – online coordination meeting)

Attendees:

1) Purpose and attendance

- The meeting opened with a quick round of introductions across participating centres (Asia + Israel), including the coordinating leads (Singapore and Hong Kong) and the IT team (Matthew and Jason, CUHK) supporting the survey platform.

2) Project progress update (translation + ethics/IRB)

- Centres involved: 14 centres in total.

- Questionnaire translation status:

  - 8 centres completed translations

  - 4 centres in progress

  - 2 centres not started

- IRB/ethics status:

  - 3 centres already approved

  - others pending / preparing submission

- Revised timeline emphasis: The group aims to submit ethics applications by March and to align data collection within the same calendar window to reduce seasonal/timing effects.

- Target data collection deadline: 26 Oct (as stated in the meeting), with the intention to complete within the year.

- Interim milestone: An ASSM interim meeting in Hong Kong (around September) where the group hopes to provide a progress update and possibly preliminary data.

3) ASSM endorsement letters

- Some centres have already received the ASSM endorsement letter; remaining requests will be compiled and sent to the ASSM president (Prof. Bahammam), with an expectation that outstanding letters will be issued within the week.

4) Authorship policy (initial paper)

- The initial publication will be the first output from the full ACROS dataset and will focus on cross-cultural comparisons of sleep patterns, obstacles, and cultural factors across Asia.

- All centres agreed (in principle) to refrain from publishing analyses from the ACROS dataset before the initial paper is accepted, to maximise impact.

- Co-author nominations:

  - Each participating centre may nominate 2 co-authors

  - The initiating/coordinating centres (Hong Kong and Singapore) may nominate 4 co-authors each

- Authorship must align with standard contribution/accountability criteria (substantial contribution, drafting/review, approval, accountability for integrity).

5) Data policy agreement (key points discussed)

- Primary ownership: Each centre retains primary ownership of data collected at its site.

- Sharing for central analysis: Centres agree to share a copy of their full dataset with initiating centres for central storage and analysis for the initial publication.

- Subsequent pooled analyses/publications: Any later shared use of pooled data will require further approval from participating centres.

- Publishing a centre’s own data: A centre may publish analyses using only its own data without needing approval from the initiating centres, but the group encouraged centres to first share proposals with the consortium to see if a pooled, higher-impact paper is possible.

6) Survey platform briefing and demo (Matthew/Jason)

Platform components

- Participant-facing questionnaire website: Each centre will have a unique survey link and consent landing page.

- Researcher-facing admin portal: For centre researchers to log in and download/view results.

Workflow

- Start from the English (Singapore) version as the baseline.

- When a centre submits its translation, the IT team will upload it to a testing site and send a test link back to the centre.

- After testing/feedback, the survey is moved to the production site and the final link is provided for distribution to participants.

- Estimated turnaround: ~2 weeks (or less) after receiving translations to get a testing link ready (depending on language complexity and back-and-forth checks).

Admin portal access and permissions

- Login via email + one-time passcode (OTP) (implementation noted as in progress).

- Each centre can only view/download its own centre’s data.

- Downloads are provided in Excel format (one column per question). The portal also supports viewing individual submissions and basic response trends.

Data hosting and security

- Hosted on AWS (Hong Kong region).

- Routine database backups planned.

- Security measures include HTTPS/TLS, encryption in transit and at rest.

Consent form and local requirements

- Participants can be enabled to download the consent form (for record-keeping).

- If a centre requires written/signature-style consent, the team can add that workflow.

- Centres may require information sheets and consent forms containing local investigator details and may need bilingual versions (e.g., English + local language). The team will support uploading whatever the IRB requires.

Validation / data-quality checks

- The platform already checks required fields and some range checks (e.g., plausible height/weight).

- Time-based logic checks (e.g., bedtime/wake-time consistency) can be added if centres provide requirements, since sleep schedules may vary widely (e.g., weekends).

7) Next steps and action items

- Centres to submit remaining co-author nominations by email (target: by end of the week).

- Centres to share any ready materials ASAP (translated questionnaire, consent/information sheets—even if some documents are still pending final translation/approval).

- IT team to continue uploading translations, issuing testing links, iterating based on feedback, then moving to production once confirmed.

- Coordinators to circulate a formalised authorship/data policy document and post it on the project website, and to upload the meeting recording/transcript for reference.