## Slide 1: ACROSS 4th Meeting
28 Sept 2026

## Slide 2: Agenda
Introduction
Progress updates: IRB/Translation/Data collection
Timeline update
Author/Data policy reminder
AOB

## Slide 3: Study progress
12 countries/regions 16 centres
Chart: IRB
IRB approved | 8
IRB in process | 4
Chart: Survey Translation
using original | 1
translated | 11
Chart: Online Survey Platform
using own platform | 2
Live | 6
testing | 4

## Slide 4: Study progress
12 countries/regions 16 centres
Chart: Data Collection
Completed | 1
Started | 5
Not yet started | 6

## Slide 5: Agenda
Introduction
Progress updates: IRB/Translation/Data collection
Timeline update
Author/Data policy reminder
AOB

## Slide 6: Timeline
 | Original timeline | Revised timeline
Final survey shared | 6 Oct 2025 | Done
Translation/IRB application | Oct-Dec 2025 | Mar 2026 (submitted)
Data collection | Jan –June 2026 | Upon IRB approval - Oct 2026
We propose to extend data collection to 31 December 2026

## Slide 7: Agenda
Introduction
Progress updates: IRB/Translation/Data collection
Timeline update
Data policy reminder
AOB

## Slide 8
5) Author number will be capped at six (6) per country/region

## Slide 10
5) Subsequent publications based on each centre’s own data are allowed, after seeking/prioritizing joint publications.

## Slide 11: Agenda
Introduction
Progress updates: IRB/Translation/Data collection
Timeline update
Author/Data policy reminder
AOB